# 2024 CoC Renewal Project Evaluations Schedule of Events

| Timeframe | Tasks |
| --- | --- |
| Week of April 1st | Memo and requirements for submission released |
| April 5th 9:00am | CoC Competition Evaluation Workgroup Review and Approval of Scoring |
| April 11th | Funding & Evaluation Committee Approval of Recommended scoring |
| April 24th | Report to Homeless Coalition Board on FY24 Process and Approval of Scoring |
| May 1st | Renewal documentation due by 5:00pm |
| May 3rd | Renewal Documentation provided to CoC Competition Evaluation Workgroup for review |
| Week of May 13th | Preliminary review of renewal documentation completed |
| Week of May 13th | CoC Competition Evaluation Workgroup Meeting – Review of Renewal Documents and initial scoring |
| May 20th – June 3rd | Site visits to all programs |
| Week of June 3rd | CoC Competition Evaluation Workgroup evaluation of renewal projects completed and any recommendations for Corrective Action Plans |
| June 13th | Funding & Evaluation Committee Approval of Renewal Project Preliminary Scoring and Corrective Action Plans (if applicable) |
| June 26th | Final report to Homeless Coalition Board for 2024 Preliminary Renewal Project Scoring and Corrective Action Plans (if Applicable) |
| May-July TBD* | Continuum of Care NOFO released |
| July TBD* | Local Request for Proposals for new projects released |
| August TBD* | Rating and Ranking of New and Renewal Projects by CoC Competition Evaluation Workgroup |
| August TBD | Approval of Rating and Ranking of New and Renewal Projects by the Funding & Evaluation Committee |
| August-September TBD* | Final Rating and Ranking of New and Renewal Projects by Homeless Coalition Board and Submission of CoC NOFO |

*HUD does not have a specific date in which the CoC Competition NOFO Is released or due for submission. The timeline above is an estimate of release and approval based on previous funding years and is subject to change.